## Sheet1 (2)
Tasks | Notes | Status | Assigned to
Pre-cutover Tasks
Install SQL Server on Target Server
Install SSMS
Configure Memory
Target server AWS EC2 turn on trace flag 1800, 1118, 1117
Configure DB Mail
Add all Logins and users
Check Trace Flags
Tempdb Autogrowth
instant_file_initialization_enabled
Add multiple files on Tempdb
Lock Pages in memory
Create Databases on proper drives
Change recovery mode to FULL on all user databases
Change auto growth on all user databases
Change DBOwner
Check Compatibilty(Keep it same as source) saved in a DBs compatibility sheet in this document
sync databases to target
Setup Distribution database
Setup test Publication and Subscription(Tested alter, insert,update) Subscriber DB2001,DB1025
Capture traffic(select statements) to build cache on new server
Add Linked servers on target(get passwords for accounts to create linked servers)
Add server trigger tr_MScdc_db_ddl_event on target
Script out Assemblies
add assembly on SSISDB
Backup Location
Implement OLA scripts for backup process
Add new EC2 on Solarwinds
Saved DB2000 scripts on new target
Gather scripts to add replication on Cutover Day
Add all SSIS packages under SSISDB catalog to Target
Connectivity test in the DSN config with the failover simulation
DB1025 - Move Reporting services to DB2000 if they are in use, check on SSRS that is on DB1025
DB1026 is subscriber of DB1025
Move IPE database from DB2009 to DB2000
Team members needed for testing on Cutover Day
Day Before Cutover
Script all jobs on source DB2000 and add them to Target server
Script all logins
Cutover Day Tasks
First change DB mirroring to Synchronous and Failover DBs to target. Scripts are save on the target server in T drive
Add replication scripts during cutover.Add publications and subscriptions
Add all sql agent jobs, owner should be FLXPRD\sql_jobs
Check Compatibilty(Keep it same as source) saved in a DBs compatibility sheet in this document
Check CLRs, assemblies on source under each database- Saved DB2000 assemblies in sheet DB2000_Assemblies
Run update stats job after cutover @4pm after cutover
Watch all sql agent jobs
Run Backups jobs
Have script ready to fix orphan users
Post Cutover Tasks
Watch Jobs after cutover
Create Update Statisics Job on target server
Create Database Backup Maintenance jobs using Ola Scripts